## Requirements
Req ID | Process Area | Description | Priority | MoSCoW | Pre-Score | Pre-Score Notes
REQ-001 | Customer Onboarding | Digital KYC verification with biometric identity checks | High | Must | Full Fit | T24 Digital KYC module supports biometric verification natively
REQ-002 | Customer Onboarding | Automated PEP and sanctions screening during onboarding | High | Must | Full Fit | Compliance screening module includes PEP/sanctions lists
REQ-003 | Account Management | Multi-currency account opening with real-time FX conversion | Medium | Should | Partial Fit | Multi-currency supported; real-time FX requires integration
REQ-008 | Lending | Dynamic interest rate adjustment based on risk profile changes | Medium | Should | No Fit | Dynamic rate adjustment not supported in standard product
REQ-010 | Reporting | Real-time management dashboards with drill-down capability | Medium | Could | No Fit | Standard reports are batch-based; no real-time drill-down

## Workshop Scoring
Req ID | Description | Fit Rating | Gap Description | Resolution Type | Effort (Days) | Risk | Notes | Parking Lot?
REQ-001 | Digital KYC with biometric checks | Full Fit |  | Configuration | 5 | Low | Standard module confirmed by Temenos SME via live demo | No
REQ-002 | PEP and sanctions screening | Full Fit |  | Configuration | 3 | Low | Compliance module demonstrated; lists refreshed daily | No
REQ-003 | Multi-currency with real-time FX | Partial Fit | Platform supports multi-currency but FX rates require external provider integration | Extension | 15 | Medium | Need FX provider selection before final estimate | No
REQ-008 | Dynamic interest rate adjustment | No Fit | Platform supports rate changes via batch but not event-driven rate adjustment based on real-time risk events | Customisation | 40 | High | Candidate for CUS-001; score below 5.0 expected | No
REQ-010 | Real-time dashboards with drill-down | No Fit | Standard reports are batch-based; drill-down requires custom UI layer over reporting APIs | Customisation | 35 | Medium | Candidate for CUS-002; UI-only customisation | No

## Customisation Scoring
CUS ID | Req ID | Description | Type | Upgrade Compat (30%) | Business Crit (25%) | TCO (20%) | Workaround Feas (15%) | Impl Risk (10%) | Weighted Score | Threshold | Approver | Status
CUS-001 | REQ-008 | Dynamic rate adjustment based on real-time risk events | Core Logic | 3 | 8 | 4 | 2 | 5 |  |  | Steering Committee | Proposed
CUS-002 | REQ-010 | Real-time management dashboard with drill-down analytics | UI | 7 | 6 | 7 | 3 | 6 |  |  | Design Authority | Under Review

## Parking Lot
Item # | Req ID | Description | Reason | Owner | Deadline | Status
1 | REQ-012 | Legacy mainframe data sync during dual-run — need schema and volume info | Missing Info | Data Migration Lead | 2026-03-22 | Open